## Sheet1
order | time_point | name | sub_name | traits | assigned_to | start | end | days | comments
1 | 0 | UAV 0 | Image |  | Peter | 2025-10-20 | 2025-10-22 | 3
2 | 0 | Stand Count | Stand | establishment | Mirza, Adrian, Peter | 2025-10-22 | 2025-10-24 | 3
3 | 1 | Growth 1 | Height | oat_height_t1, pea_height_t1 | Mirza, Adrian, Peter | 2025-11-03 | 2025-11-07 | 5
4 | 1 | UAV 1 | UAV |  | Peter | 2025-11-03 | 2025-11-07 | 5
5 | 1 | Research 1 | Image |  | Mirza, Adrian | 2025-11-03 | 2025-11-07 | 5
6 | 1 | Calibrator 1 | Biomass | oat_biomass_t1, pea_biomass_t1, weed_biomass_t1 | Mirza, Adrian, Peter | 2025-11-03 | 2025-11-07 | 5
7 | 1 | Maintenance 1 | Data, Field |  | Mirza, Adrian, Peter | 2025-11-03 | 2025-11-07 | 5
8 | 1.5 | Flowering | Phenology | pea_flowering | Mirza | 2026-06-05 | 2026-06-25 | 21
9 | 1.5 | Heading | Phenology | oat_heading | Mirza | 2026-06-05 | 2026-06-25 | 21
10 | 2 | Growth 2 | Height | oat_height_t2, pea_height_t2 | Mirza, Adrian, Peter | 2026-05-20 | 2026-05-28 | 9
11 | 2 | UAV 2 | UAV |  | Peter | 2026-05-20 | 2026-05-28 | 9
12 | 2 | Research 2 | PM3D Research |  | Mirza, Adrian | 2026-05-20 | 2026-05-28 | 9
13 | 2 | Calibrator 2 | PM3D Calibrator | oat_biomass_t2, pea_biomass_t2, weed_biomass_t2 | Mirza, Adrian, Peter | 2026-05-20 | 2026-05-28 | 9
14 | 2 | Maintenance 2 | Data, Field |  | Mirza, Adrian, Peter | 2026-05-20 | 2026-05-28 | 9
15 | 2.5 | Maturity | Phenology | maturity | Mirza | 2026-06-18 | 2026-07-08 | 21
16 | 3 | Growth 3 | Height, canopy | oat_height_t3, pea_height_t3 | Mirza, Adrian, Peter | 2026-06-10 | 2026-06-18 | 9
17 | 3 | UAV 3 | UAV |  | Peter | 2026-06-10 | 2026-06-18 | 9
18 | 3 | Research 3 | Image |  | Mirza, Adrian | 2026-06-10 | 2026-06-18 | 9
19 | 3 | Calibrator 3 | Biomass | oat_biomass_t3, pea_biomass_t3, weed_biomass_t3 | Mirza, Adrian, Peter | 2026-06-10 | 2026-06-18 | 9
20 | 3 | Maintenance 3 | Data, Field |  | Mirza, Adrian, Peter | 2026-06-10 | 2026-06-18 | 9
21 | 4 | UAV 4 | UAV |  | Mirza, Adrian, Peter | 2026-07-10 | 2026-07-15 | 6
22 | 4 | Height | Harvest | oat_height_t4, pea_height_t4 | Peter | 2026-07-10 | 2026-07-15 | 6
23 | 4 | Lodging | Harvest | lodging | Mirza, Adrian | 2026-07-10 | 2026-07-15 | 6
24 | 4 | Grain Harvest | Harvest |  | Mirza, Adrian, Peter | 2026-07-10 | 2026-07-15 | 6
25 | 5 | Grain Separation | Harvest | oat_grain_weight, pea_grain_weight | Mirza, Adrian, Peter | 2026-07-20 | 2026-08-01 | 13
26 | 6 | Peter
27 | 6 | Jean-Luc
28 | 6 | Mirza
29 | 6 | Leah
30 | 6 | Adrian